## SDIRA Timeline
SDIRA CONVERSION TIMELINE PLANNER
The Wealth Shift by J. Marque — Module 5, Calculator 4
Week | Milestone | Status | Notes
Wk 1-2 | Research SDIRA custodians (compare 3+) |  | See Module 2 custodian comparison
Wk 2-3 | Open SDIRA account |  | Application + ID verification
Wk 3-4 | Initiate rollover from current 401(k)/IRA |  | Direct trustee-to-trustee transfer
Wk 4-6 | Rollover processing (custodian timeline) |  | Typically 2-4 weeks
Wk 5-7 | Funds available in SDIRA |  | Confirm with custodian
Wk 6-8 | Identify target property |  | Apply buy box criteria
Wk 8-10 | Property due diligence |  | Inspection, appraisal, title
Wk 10-12 | Submit offer through SDIRA custodian |  | Custodian signs on behalf of IRA
Wk 12-16 | Custodian approval + title review |  | May take 1-2 weeks
Wk 16-20 | Close on property |  | SDIRA is the buyer, not you
Wk 20-24 | Property placed with manager + first rent |  | Cash flow begins
TOTAL TIMELINE: 4-6 MONTHS from decision to first cash flow
Money Decoded by J. Marque ¦ moneydecodedbooks.com